## Build Tracker
AWAT - Build Tracker
CTDI - Alburtis
Record # | PO Number | CTDI Status | Delivered Date | Cabinet Start Date | Cabinet Complete Date | Transfer Out Date
1 | 8000123456 | Complete | 2025-01-01 | 2025-01-01 | 2025-08-27 | 2025-08-27
2 | 8000182814 | Complete | 2025-09-19 | 2025-09-22 | 2025-09-30 | 2025-09-30
3 | 8000183203 | Complete | 2025-09-23 | 2025-09-24 | 2025-10-01 | 2025-10-20
4 | 8000183204 | Complete | 2025-09-23 | 2025-09-24 | 2025-10-03 | 2025-10-20
5 | 8000184211 | Complete | 2025-09-26 | 2025-10-02 | 2025-10-03 | 2025-10-20
6 | 8000184210 | Complete | 2025-09-26 | 2025-10-02 | 2025-10-06 | 2025-10-20
7 | 8000189212 | Complete | 2025-10-09 | 2025-10-09 | 2025-10-13 | 2025-10-28
8 | 8000189213 | Complete | 2025-10-09 | 2025-10-09 | 2025-10-28 | 2025-10-28
9 | 8000189805 | Complete | 2025-10-15 | 2025-10-15 | 2025-11-10 | 2025-11-10 |  | `
10 | 8000189807 | Complete | 2025-10-20 | 2025-10-21 | 2025-11-10 | 2025-11-10
11 | 8000189808 | Complete | 2025-10-20 | 2025-10-21 | 2025-11-10 | 2025-11-10
12 | 8000189809 | Complete | 2025-10-23 | 2025-10-23 | 2025-11-26 | 2025-11-26
13 | 8000199908 | Complete | 2025-11-04 | 2025-11-04 | 2025-11-26 | 2025-11-26
14 | 8000199909 | Complete | 2025-11-04 | 2025-11-04 | 2025-11-10 | 2025-11-10
15 | 8000199975 | Complete | 2025-11-04 | 2025-11-04 | 2025-11-26 | 2025-11-26
16 | 8000199976 | Complete | 2025-11-05 | 2025-11-06 | 2025-11-26 | 2025-11-26
17 | 8000199977 | Complete | 2025-11-05 | 2025-11-06 | 2025-11-26 | 2025-11-26
18 | 8000207077 | Complete | 2025-11-24 | 2025-11-25 | 2025-12-15 | 2025-12-18
19 | 8000207079 | Complete | 2025-11-24 | 2025-11-25 | 2025-12-15 | 2025-12-18
20 | 8000207080 | Complete | 2025-11-26 | 2025-11-25 | 2025-11-26 | 2025-11-26
21 | 8000207081 | Complete | 2025-11-24 | 2025-11-25 | 2025-12-26 | 2025-12-29
22 | 8000207788 | Complete | 2025-12-10 | 2025-12-10 | 2025-12-15 | 2025-12-18
23 | 8000207789 | Complete | 2025-12-10 | 2025-12-10 | 2025-12-15 | 2025-12-18
24 | 8000207790 | Complete | 2025-12-10 | 2025-12-10 | 2025-12-15 | 2025-12-18
25 | 8000207791 | Complete | 2025-12-10 | 2025-12-10 | 2025-12-15 | 2025-12-18
26 | 8000207880 | Complete | 2025-12-15 | 2025-12-18 | 2026-01-06 | 2026-01-09
27 | 8000207881 | Complete | 2025-12-15 | 2025-12-18 | 2026-01-07 | 2026-01-09
28 | 8000207883 | Complete | 2025-12-15 | 2025-11-25 | 2025-12-26 | 2025-12-29
29 | 8000207884 | Complete | 2025-12-15 | 2025-12-18 | 2026-01-07 | 2026-01-09
30 | 8000214797 | Complete | 2026-01-02 | 2026-01-05 | 2026-01-06 | 2026-01-09
31 | 8000214798 | Complete | 2026-01-02 | 2026-01-05 | 2026-01-08 | 2026-01-09
32 | 8000214799 | Complete | 2026-01-02 | 2026-01-05 | 2026-01-08 | 2026-01-09
33 | 8000214800 | Complete | 2026-01-02 | 2026-01-05 | 2026-01-09 | 2026-01-09
34 | 8000214801 | Complete | 2026-01-02 | 2026-01-05 | 2026-01-13 | 2026-01-16
35 | 8000216866 | Complete | 2026-01-14 | 2026-01-14 | 2026-01-16 | 2026-01-16
36 | 8000216867 | Complete | 2026-01-14 | 2026-01-14 | 2026-02-02 | 2026-02-04 | Defective HVAC, Charles alerted and remedy action being scheduled (Fixed- 2-2-2026)
37 | 8000216868 | Complete | 2026-01-14 | 2026-01-19 | 2026-01-20 | 2026-01-26
38 | 8000216869 | Complete | 2026-01-14 | 2026-01-14 | 2026-01-19 | 2026-01-26
39 | 8000216870 | Complete | 2026-01-14 | 2026-01-19 | 2026-01-20 | 2026-01-26
40 | 8000216864 | Complete | 2026-01-14 | 2026-01-14 | 2026-01-16 | 2026-01-26
41 | 8000218117 | Complete | 2026-01-20 | 2026-01-23 | 2026-01-27 | 2026-01-30
42 | 8000218118 | Complete | 2026-01-20 | 2026-01-23 | 2026-01-28 | 2026-01-30
43 | 8000218119 | Complete | 2026-01-20 | 2026-01-20 | 2026-01-22 | 2026-01-26
44 | 8000218121 | Complete | 2026-01-20 | 2026-01-20 | 2026-01-22 | 2026-01-26
45 | 8000218122 | Complete | 2026-01-20 | 2026-01-22 | 2026-01-28 | 2026-01-30
46 | 8000218124 | Complete | 2026-01-20 | 2026-01-22 | 2026-01-26 | 2026-01-28
47 | 8000223193 | Complete | 2026-01-27 | 2026-01-29 | 2026-01-30 | 2026-02-02
48 | 8000223222 | Complete | 2026-01-27 | 2026-01-29 | 2026-02-04 | 2026-02-05
49 | 8000223244 | Complete | 2026-01-27 | 2026-01-29 | 2026-02-20 | 2026-02-23 | Missing Alarm Sticker
50 | 8000223262 | Complete | 2026-01-27 | 2026-01-28 | 2026-01-30 | 2026-02-02
51 | 8000223278 | Complete | 2026-01-27 | 2026-01-30 | 2026-02-05 | 2026-02-09
52 | 8000223299 | Complete | 2026-01-27 | 2026-01-28 | 2026-02-02 | 2026-02-04
53 | 8000227621 | Complete | 2026-02-03 | 2026-02-05 | 2026-02-10 | 2026-02-11
54 | 8000227623 | Complete | 2026-02-03 | 2026-02-06 | 2026-02-12 | 2026-02-16
55 | 8000227624 | Complete | 2026-02-03 | 2026-02-06 | 2026-02-12 | 2026-02-16
56 | 8000227625 | Complete | 2026-02-03 | 2026-02-03 | 2026-02-10 | 2026-02-11
57 | 8000227626 | Complete | 2026-02-03 | 2026-02-04 | 2026-02-10 | 2026-02-11
58 | 8000227627 | Complete | 2026-02-03 | 2026-02-06 | 2026-02-10 | 2026-02-11
59 | 8000228117 | Complete | 2026-02-09 | 2026-02-16 | 2026-02-18 | 2026-02-19
60 | 8000228119 | Complete | 2026-02-09 | 2026-02-11 | 2026-02-26 | 2026-02-27 | Damaged Siteboss
61 | 8000228139 | Complete | 2026-02-09 | 2026-02-13 | 2026-02-17 | 2026-02-17
62 | 8000228140 | Complete | 2026-02-09 | 2026-02-12 | 2026-02-13 | 2026-02-16
63 | 8000228141 | Complete | 2026-02-09 | 2026-02-13 | 2026-02-17 | 2026-02-17
64 | 8000228142 | Complete | 2026-02-09 | 2026-02-12 | 2026-02-13 | 2026-02-16
65 | 8000229902 | Complete | 2026-02-18 | 2026-02-23 | 2026-02-24 | 2026-02-26
66 | 8000230020 | Complete | 2026-02-18 | 2026-02-26 | 2026-03-02 | 2026-03-03
67 | 8000230227 | Complete | 2026-02-18 | 2026-02-27 | 2026-03-13 | 2026-03-30
68 | 8000231758 | Complete | 2026-02-18 | 2026-02-18 | 2026-02-20 | 2026-02-23
69 | 8000231759 | Complete | 2026-02-18 | 2026-02-18 | 2026-02-24 | 2026-02-26
70 | 8000231762 | Complete | 2026-02-18 | 2026-02-23 | 2026-02-26 | 2026-02-27
71 | 8000232645 | Complete | 2026-02-24 | 2026-02-27 | 2026-03-16 | 2026-03-30
72 | 8000232647 | Complete | 2026-02-24 | 2026-03-10 | 2026-03-16 | 2026-03-30
73 | 8000232648 | Complete | 2026-02-24 | 2026-02-26 | 2026-03-04 | 2026-03-05
74 | 8000232866 | Complete | 2026-02-24 | 2026-02-26 | 2026-03-04 | 2026-03-05
75 | 8000232868 | Complete | 2026-02-24 | 2026-02-27 | 2026-03-04 | 2026-03-05
76 | 8000232869 | Complete | 2026-02-24 | 2026-03-02 | 2026-03-06 | 2026-03-11
77 | 8000234305 | Complete | 2026-03-02 | 2026-03-03 | 2026-03-06 | 2026-03-11
78 | 8000234458 | Complete | 2026-03-02 | 2026-03-03 | 2026-03-11 | 2026-03-30
79 | 8000234698 | In Process | 2026-03-02 | 2026-03-04
80 | 8000234700 | Complete | 2026-03-02 | 2026-03-04 | 2026-03-16 | 2026-03-30
81 | 8000234705 | Complete | 2026-03-02 | 2026-03-06 | 2026-03-11 | 2026-03-30
82 | 8000234711 | Complete | 2026-03-02 | 2026-03-10 | 2026-03-16 | 2026-03-30
83 | 8000244361 | In Process |  |  |  |  | Forward Engineering Cabinet, need to confirm receipt date
84 | 8000237138 | In Process |  |  |  |  | Forward Engineering Cabinet, need to confirm receipt date
85 | 8000206888 | In Process |  |  |  |  | Forward Engineering Cabinet, need to confirm receipt date
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113

## Staffing
AWAT - Staffing
Month | Date | Day of Week | Working Day # | Staff Headcount | * Anyone working their time to AWAT
2026-01-01 | 2026-01-01 | Thurs | 1 | 0
2026-01-01 | 2026-01-02 | Fri | 2
2026-01-01 | 2026-01-03 | Sat | 2
2026-01-01 | 2026-01-04 | Sun | 2
2026-01-01 | 2026-01-05 | Mon | 3
2026-01-01 | 2026-01-06 | Tues | 4
2026-01-01 | 2026-01-07 | Wed | 5
2026-01-01 | 2026-01-08 | Thurs | 6
2026-01-01 | 2026-01-09 | Fri | 7
2026-01-01 | 2026-01-10 | Sat | 7
2026-01-01 | 2026-01-11 | Sun | 7
2026-01-01 | 2026-01-12 | Mon | 8 | 3
2026-01-01 | 2026-01-13 | Tues | 9 | 3
2026-01-01 | 2026-01-14 | Wed | 10 | 2.6 - Greg Left Early
2026-01-01 | 2026-01-15 | Thurs | 11 | 3
2026-01-01 | 2026-01-16 | Fri | 12 | 3
2026-01-01 | 2026-01-17 | Sat | 12
2026-01-01 | 2026-01-18 | Sun | 12
2026-01-01 | 2026-01-19 | Mon | 13 | 3
2026-01-01 | 2026-01-20 | Tues | 14 | 2
2026-01-01 | 2026-01-21 | Wed | 15 | 3
2026-01-01 | 2026-01-22 | Thurs | 16 | 3
2026-01-01 | 2026-01-23 | Fri | 17 | 3
2026-01-01 | 2026-01-24 | Sat | 17
2026-01-01 | 2026-01-25 | Sun | 17
2026-01-01 | 2026-01-26 | Mon | 18 | 1
2026-01-01 | 2026-01-27 | Tues | 19 | 3
2026-01-01 | 2026-01-28 | Wed | 20 | 3
2026-01-01 | 2026-01-29 | Thurs | 21 | 3
2026-01-01 | 2026-01-30 | Fri | 22 | 3
2026-01-01 | 2026-01-31 | Sat | 22
2026-02-01 | 2026-02-01 | Sun | 22
2026-02-01 | 2026-02-02 | Mon | 23 | 2
2026-02-01 | 2026-02-03 | Tues | 24 | 3
2026-02-01 | 2026-02-04 | Wed | 25 | 3
2026-02-01 | 2026-02-05 | Thurs | 26 | 2.5
2026-02-01 | 2026-02-06 | Fri | 27 | 2
2026-02-01 | 2026-02-07 | Sat | 27
2026-02-01 | 2026-02-08 | Sun | 27
2026-02-01 | 2026-02-09 | Mon | 28 | 3
2026-02-01 | 2026-02-10 | Tues | 29 | 3
2026-02-01 | 2026-02-11 | Wed | 30 | 2.7
2026-02-01 | 2026-02-12 | Thurs | 31 | 3
2026-02-01 | 2026-02-13 | Fri | 32 | 2.7
2026-02-01 | 2026-02-14 | Sat | 32
2026-02-01 | 2026-02-15 | Sun | 32
2026-02-01 | 2026-02-16 | Mon | 33 | 3
2026-02-01 | 2026-02-17 | Tues | 34 | 3
2026-02-01 | 2026-02-18 | Wed | 35 | 3
2026-02-01 | 2026-02-19 | Thurs | 36 | 3
2026-02-01 | 2026-02-20 | Fri | 37 | 2.6
2026-02-01 | 2026-02-21 | Sat | 37
2026-02-01 | 2026-02-22 | Sun | 37
2026-02-01 | 2026-02-23 | Mon | 38 | 3
2026-02-01 | 2026-02-24 | Tues | 39 | 4
2026-02-01 | 2026-02-25 | Wed | 40 | 4
2026-02-01 | 2026-02-26 | Thurs | 41 | 2.2
2026-02-01 | 2026-02-27 | Fri | 42 | 2
2026-02-01 | 2026-02-28 | Sat | 42
2026-03-01 | 2026-03-01 | Sun | 42
2026-03-01 | 2026-03-02 | Mon | 43 | 5
2026-03-01 | 2026-03-03 | Tues | 44 | 5
2026-03-01 | 2026-03-04 | Wed | 45 | 5
2026-03-01 | 2026-03-05 | Thurs | 46 | 5
2026-03-01 | 2026-03-06 | Fri | 47 | 5
2026-03-01 | 2026-03-07 | Sat | 47
2026-03-01 | 2026-03-08 | Sun | 47
2026-03-01 | 2026-03-09 | Mon | 48 | 5
2026-03-01 | 2026-03-10 | Tues | 49 | 5
2026-03-01 | 2026-03-11 | Wed | 50 | 5
2026-03-01 | 2026-03-12 | Thurs | 51 | 5
2026-03-01 | 2026-03-13 | Fri | 52 | 4
2026-03-01 | 2026-03-14 | Sat | 52
2026-03-01 | 2026-03-15 | Sun | 52
2026-03-01 | 2026-03-16 | Mon | 53 | 5
2026-03-01 | 2026-03-17 | Tues | 54 | 5
2026-03-01 | 2026-03-18 | Wed | 55 | 4
2026-03-01 | 2026-03-19 | Thurs | 56 | 5
2026-03-01 | 2026-03-20 | Fri | 57 | 5
2026-03-01 | 2026-03-21 | Sat | 57
2026-03-01 | 2026-03-22 | Sun | 57
2026-03-01 | 2026-03-23 | Mon | 58 | 5
2026-03-01 | 2026-03-24 | Tues | 59 | 5
2026-03-01 | 2026-03-25 | Wed | 60 | 5
2026-03-01 | 2026-03-26 | Thurs | 61 | 5
2026-03-01 | 2026-03-27 | Fri | 62 | 4
2026-03-01 | 2026-03-28 | Sat | 62
2026-03-01 | 2026-03-29 | Sun | 62
2026-03-01 | 2026-03-30 | Mon | 63 | 3
2026-03-01 | 2026-03-31 | Tues | 64 | 3
2026-04-01 | 2026-04-01 | Wed | 65 | 3
2026-04-01 | 2026-04-02 | Thurs | 66
2026-04-01 | 2026-04-03 | Fri | 67
2026-04-01 | 2026-04-04 | Sat | 67
2026-04-01 | 2026-04-05 | Sun | 67
2026-04-01 | 2026-04-06 | Mon | 68
2026-04-01 | 2026-04-07 | Tues | 69
2026-04-01 | 2026-04-08 | Wed | 70
2026-04-01 | 2026-04-09 | Thurs | 71
2026-04-01 | 2026-04-10 | Fri | 72
2026-04-01 | 2026-04-11 | Sat | 72
2026-04-01 | 2026-04-12 | Sun | 72
2026-04-01 | 2026-04-13 | Mon | 73
2026-04-01 | 2026-04-14 | Tues | 74
2026-04-01 | 2026-04-15 | Wed | 75
2026-04-01 | 2026-04-16 | Thurs | 76
2026-04-01 | 2026-04-17 | Fri | 77
2026-04-01 | 2026-04-18 | Sat | 77
2026-04-01 | 2026-04-19 | Sun | 77
2026-04-01 | 2026-04-20 | Mon | 78
2026-04-01 | 2026-04-21 | Tues | 79
2026-04-01 | 2026-04-22 | Wed | 80
2026-04-01 | 2026-04-23 | Thurs | 81
2026-04-01 | 2026-04-24 | Fri | 82
2026-04-01 | 2026-04-25 | Sat | 82
2026-04-01 | 2026-04-26 | Sun | 82
2026-04-01 | 2026-04-27 | Mon | 83
2026-04-01 | 2026-04-28 | Tues | 84
2026-04-01 | 2026-04-29 | Wed | 85
2026-04-01 | 2026-04-30 | Thurs | 86
2026-05-01 | 2026-05-01 | Fri | 87
2026-05-01 | 2026-05-02 | Sat | 87
2026-05-01 | 2026-05-03 | Sun | 87
2026-05-01 | 2026-05-04 | Mon | 88
2026-05-01 | 2026-05-05 | Tues | 89
2026-05-01 | 2026-05-06 | Wed | 90
2026-05-01 | 2026-05-07 | Thurs | 91
2026-05-01 | 2026-05-08 | Fri | 92
2026-05-01 | 2026-05-09 | Sat | 92
2026-05-01 | 2026-05-10 | Sun | 92
2026-05-01 | 2026-05-11 | Mon | 93
2026-05-01 | 2026-05-12 | Tues | 94
2026-05-01 | 2026-05-13 | Wed | 95
2026-05-01 | 2026-05-14 | Thurs | 96
2026-05-01 | 2026-05-15 | Fri | 97
2026-05-01 | 2026-05-16 | Sat | 97
2026-05-01 | 2026-05-17 | Sun | 97
2026-05-01 | 2026-05-18 | Mon | 98
2026-05-01 | 2026-05-19 | Tues | 99
2026-05-01 | 2026-05-20 | Wed | 100
2026-05-01 | 2026-05-21 | Thurs | 101
2026-05-01 | 2026-05-22 | Fri | 102
2026-05-01 | 2026-05-23 | Sat | 102
2026-05-01 | 2026-05-24 | Sun | 102
2026-05-01 | 2026-05-25 | Mon | 103
2026-05-01 | 2026-05-26 | Tues | 104
2026-05-01 | 2026-05-27 | Wed | 105
2026-05-01 | 2026-05-28 | Thurs | 106
2026-05-01 | 2026-05-29 | Fri | 107
2026-05-01 | 2026-05-30 | Sat | 107
2026-05-01 | 2026-05-31 | Sun | 107
2026-06-01 | 2026-06-01 | Mon | 108
2026-06-01 | 2026-06-02 | Tues | 109
2026-06-01 | 2026-06-03 | Wed | 110
2026-06-01 | 2026-06-04 | Thurs | 111
2026-06-01 | 2026-06-05 | Fri | 112
2026-06-01 | 2026-06-06 | Sat | 112
2026-06-01 | 2026-06-07 | Sun | 112
2026-06-01 | 2026-06-08 | Mon | 113
2026-06-01 | 2026-06-09 | Tues | 114
2026-06-01 | 2026-06-10 | Wed | 115
2026-06-01 | 2026-06-11 | Thurs | 116
2026-06-01 | 2026-06-12 | Fri | 117
2026-06-01 | 2026-06-13 | Sat | 117
2026-06-01 | 2026-06-14 | Sun | 117
2026-06-01 | 2026-06-15 | Mon | 118
2026-06-01 | 2026-06-16 | Tues | 119
2026-06-01 | 2026-06-17 | Wed | 120
2026-06-01 | 2026-06-18 | Thurs | 121
2026-06-01 | 2026-06-19 | Fri | 122
2026-06-01 | 2026-06-20 | Sat | 122
2026-06-01 | 2026-06-21 | Sun | 122
2026-06-01 | 2026-06-22 | Mon | 123
2026-06-01 | 2026-06-23 | Tues | 124
2026-06-01 | 2026-06-24 | Wed | 125
2026-06-01 | 2026-06-25 | Thurs | 126
2026-06-01 | 2026-06-26 | Fri | 127
2026-06-01 | 2026-06-27 | Sat | 127
2026-06-01 | 2026-06-28 | Sun | 127
2026-06-01 | 2026-06-29 | Mon | 128
2026-06-01 | 2026-06-30 | Tues | 129
2026-07-01 | 2026-07-01 | Wed | 130
2026-07-01 | 2026-07-02 | Thurs | 131
2026-07-01 | 2026-07-03 | Fri | 132
2026-07-01 | 2026-07-04 | Sat | 132
2026-07-01 | 2026-07-05 | Sun | 132
2026-07-01 | 2026-07-06 | Mon | 133
2026-07-01 | 2026-07-07 | Tues | 134
2026-07-01 | 2026-07-08 | Wed | 135
2026-07-01 | 2026-07-09 | Thurs | 136
2026-07-01 | 2026-07-10 | Fri | 137
2026-07-01 | 2026-07-11 | Sat | 137
2026-07-01 | 2026-07-12 | Sun | 137
2026-07-01 | 2026-07-13 | Mon | 138
2026-07-01 | 2026-07-14 | Tues | 139
2026-07-01 | 2026-07-15 | Wed | 140
2026-07-01 | 2026-07-16 | Thurs | 141
2026-07-01 | 2026-07-17 | Fri | 142
2026-07-01 | 2026-07-18 | Sat | 142
2026-07-01 | 2026-07-19 | Sun | 142
2026-07-01 | 2026-07-20 | Mon | 143
2026-07-01 | 2026-07-21 | Tues | 144
2026-07-01 | 2026-07-22 | Wed | 145
2026-07-01 | 2026-07-23 | Thurs | 146
2026-07-01 | 2026-07-24 | Fri | 147
2026-07-01 | 2026-07-25 | Sat | 147
2026-07-01 | 2026-07-26 | Sun | 147
2026-07-01 | 2026-07-27 | Mon | 148
2026-07-01 | 2026-07-28 | Tues | 149
2026-07-01 | 2026-07-29 | Wed | 150
2026-07-01 | 2026-07-30 | Thurs | 151
2026-07-01 | 2026-07-31 | Fri | 152
2026-08-01 | 2026-08-01 | Sat | 152
2026-08-01 | 2026-08-02 | Sun | 152
2026-08-01 | 2026-08-03 | Mon | 153
2026-08-01 | 2026-08-04 | Tues | 154
2026-08-01 | 2026-08-05 | Wed | 155
2026-08-01 | 2026-08-06 | Thurs | 156
2026-08-01 | 2026-08-07 | Fri | 157
2026-08-01 | 2026-08-08 | Sat | 157
2026-08-01 | 2026-08-09 | Sun | 157
2026-08-01 | 2026-08-10 | Mon | 158
2026-08-01 | 2026-08-11 | Tues | 159
2026-08-01 | 2026-08-12 | Wed | 160
2026-08-01 | 2026-08-13 | Thurs | 161
2026-08-01 | 2026-08-14 | Fri | 162
2026-08-01 | 2026-08-15 | Sat | 162
2026-08-01 | 2026-08-16 | Sun | 162
2026-08-01 | 2026-08-17 | Mon | 163
2026-08-01 | 2026-08-18 | Tues | 164
2026-08-01 | 2026-08-19 | Wed | 165
2026-08-01 | 2026-08-20 | Thurs | 166
2026-08-01 | 2026-08-21 | Fri | 167
2026-08-01 | 2026-08-22 | Sat | 167
2026-08-01 | 2026-08-23 | Sun | 167
2026-08-01 | 2026-08-24 | Mon | 168
2026-08-01 | 2026-08-25 | Tues | 169
2026-08-01 | 2026-08-26 | Wed | 170
2026-08-01 | 2026-08-27 | Thurs | 171
2026-08-01 | 2026-08-28 | Fri | 172
2026-08-01 | 2026-08-29 | Sat | 172
2026-08-01 | 2026-08-30 | Sun | 172
2026-08-01 | 2026-08-31 | Mon | 173
2026-09-01 | 2026-09-01 | Tues | 174
2026-09-01 | 2026-09-02 | Wed | 175
2026-09-01 | 2026-09-03 | Thurs | 176
2026-09-01 | 2026-09-04 | Fri | 177
2026-09-01 | 2026-09-05 | Sat | 177
2026-09-01 | 2026-09-06 | Sun | 177
2026-09-01 | 2026-09-07 | Mon | 178
2026-09-01 | 2026-09-08 | Tues | 179
2026-09-01 | 2026-09-09 | Wed | 180
2026-09-01 | 2026-09-10 | Thurs | 181
2026-09-01 | 2026-09-11 | Fri | 182
2026-09-01 | 2026-09-12 | Sat | 182
2026-09-01 | 2026-09-13 | Sun | 182
2026-09-01 | 2026-09-14 | Mon | 183
2026-09-01 | 2026-09-15 | Tues | 184
2026-09-01 | 2026-09-16 | Wed | 185
2026-09-01 | 2026-09-17 | Thurs | 186
2026-09-01 | 2026-09-18 | Fri | 187
2026-09-01 | 2026-09-19 | Sat | 187
2026-09-01 | 2026-09-20 | Sun | 187
2026-09-01 | 2026-09-21 | Mon | 188
2026-09-01 | 2026-09-22 | Tues | 189
2026-09-01 | 2026-09-23 | Wed | 190
2026-09-01 | 2026-09-24 | Thurs | 191
2026-09-01 | 2026-09-25 | Fri | 192
2026-09-01 | 2026-09-26 | Sat | 192
2026-09-01 | 2026-09-27 | Sun | 192
2026-09-01 | 2026-09-28 | Mon | 193
2026-09-01 | 2026-09-29 | Tues | 194
2026-09-01 | 2026-09-30 | Wed | 195
2026-10-01 | 2026-10-01 | Thurs | 196
2026-10-01 | 2026-10-02 | Fri | 197
2026-10-01 | 2026-10-03 | Sat | 197
2026-10-01 | 2026-10-04 | Sun | 197
2026-10-01 | 2026-10-05 | Mon | 198
2026-10-01 | 2026-10-06 | Tues | 199
2026-10-01 | 2026-10-07 | Wed | 200
2026-10-01 | 2026-10-08 | Thurs | 201
2026-10-01 | 2026-10-09 | Fri | 202
2026-10-01 | 2026-10-10 | Sat | 202
2026-10-01 | 2026-10-11 | Sun | 202
2026-10-01 | 2026-10-12 | Mon | 203
2026-10-01 | 2026-10-13 | Tues | 204
2026-10-01 | 2026-10-14 | Wed | 205
2026-10-01 | 2026-10-15 | Thurs | 206
2026-10-01 | 2026-10-16 | Fri | 207
2026-10-01 | 2026-10-17 | Sat | 207
2026-10-01 | 2026-10-18 | Sun | 207
2026-10-01 | 2026-10-19 | Mon | 208
2026-10-01 | 2026-10-20 | Tues | 209
2026-10-01 | 2026-10-21 | Wed | 210
2026-10-01 | 2026-10-22 | Thurs | 211
2026-10-01 | 2026-10-23 | Fri | 212
2026-10-01 | 2026-10-24 | Sat | 212
2026-10-01 | 2026-10-25 | Sun | 212
2026-10-01 | 2026-10-26 | Mon | 213
2026-10-01 | 2026-10-27 | Tues | 214
2026-10-01 | 2026-10-28 | Wed | 215
2026-10-01 | 2026-10-29 | Thurs | 216
2026-10-01 | 2026-10-30 | Fri | 217
2026-10-01 | 2026-10-31 | Sat | 217
2026-11-01 | 2026-11-01 | Sun | 217
2026-11-01 | 2026-11-02 | Mon | 218
2026-11-01 | 2026-11-03 | Tues | 219
2026-11-01 | 2026-11-04 | Wed | 220
2026-11-01 | 2026-11-05 | Thurs | 221
2026-11-01 | 2026-11-06 | Fri | 222
2026-11-01 | 2026-11-07 | Sat | 222
2026-11-01 | 2026-11-08 | Sun | 222
2026-11-01 | 2026-11-09 | Mon | 223
2026-11-01 | 2026-11-10 | Tues | 224
2026-11-01 | 2026-11-11 | Wed | 225
2026-11-01 | 2026-11-12 | Thurs | 226
2026-11-01 | 2026-11-13 | Fri | 227
2026-11-01 | 2026-11-14 | Sat | 227
2026-11-01 | 2026-11-15 | Sun | 227
2026-11-01 | 2026-11-16 | Mon | 228
2026-11-01 | 2026-11-17 | Tues | 229
2026-11-01 | 2026-11-18 | Wed | 230
2026-11-01 | 2026-11-19 | Thurs | 231
2026-11-01 | 2026-11-20 | Fri | 232
2026-11-01 | 2026-11-21 | Sat | 232
2026-11-01 | 2026-11-22 | Sun | 232
2026-11-01 | 2026-11-23 | Mon | 233
2026-11-01 | 2026-11-24 | Tues | 234
2026-11-01 | 2026-11-25 | Wed | 235
2026-11-01 | 2026-11-26 | Thurs | 236
2026-11-01 | 2026-11-27 | Fri | 237
2026-11-01 | 2026-11-28 | Sat | 237
2026-11-01 | 2026-11-29 | Sun | 237
2026-11-01 | 2026-11-30 | Mon | 238
2026-12-01 | 2026-12-01 | Tues | 239
2026-12-01 | 2026-12-02 | Wed | 240
2026-12-01 | 2026-12-03 | Thurs | 241
2026-12-01 | 2026-12-04 | Fri | 242
2026-12-01 | 2026-12-05 | Sat | 242
2026-12-01 | 2026-12-06 | Sun | 242
2026-12-01 | 2026-12-07 | Mon | 243
2026-12-01 | 2026-12-08 | Tues | 244
2026-12-01 | 2026-12-09 | Wed | 245
2026-12-01 | 2026-12-10 | Thurs | 246
2026-12-01 | 2026-12-11 | Fri | 247
2026-12-01 | 2026-12-12 | Sat | 247
2026-12-01 | 2026-12-13 | Sun | 247
2026-12-01 | 2026-12-14 | Mon | 248
2026-12-01 | 2026-12-15 | Tues | 249
2026-12-01 | 2026-12-16 | Wed | 250
2026-12-01 | 2026-12-17 | Thurs | 251
2026-12-01 | 2026-12-18 | Fri | 252
2026-12-01 | 2026-12-19 | Sat | 252
2026-12-01 | 2026-12-20 | Sun | 252
2026-12-01 | 2026-12-21 | Mon | 253
2026-12-01 | 2026-12-22 | Tues | 254
2026-12-01 | 2026-12-23 | Wed | 255
2026-12-01 | 2026-12-24 | Thurs | 256
2026-12-01 | 2026-12-25 | Fri | 257
2026-12-01 | 2026-12-26 | Sat | 257
2026-12-01 | 2026-12-27 | Sun | 257
2026-12-01 | 2026-12-28 | Mon | 258
2026-12-01 | 2026-12-29 | Tues | 259
2026-12-01 | 2026-12-30 | Wed | 260
2026-12-01 | 2026-12-31 | Thurs | 261
2027-01-01 | 2027-01-01 | Fri | 262
2027-01-01 | 2027-01-02 | Sat | 262
2027-01-01 | 2027-01-03 | Sun | 262
Formulas:
Month = DATE(YEAR([Date]),MONTH([Date]),1)
Date = [Date, row above]+1

## REF - Dropdowns (hidden)
Dropdowns
Build Tracker
CTDI Status
Not Received Yet
Not Started
In Process
Complete
Non-Workable

## REF - Notes (hidden)
CTDI Status
| Queued | Order Received but work has not begun
| Assembly | Cabinet is being assembled
| Test | Assembled cabinet is under test
| Rework | QC Failed and being re-worked
| Complete | CTDI has completed work & cabinet is staged to go back
| RTS | Completed cabinet has been received by K&N
Non-Workable